## Sheet1
This Calander represents the summary of each scheduled work period and meetings that were arranged for working on the project. These times do not include times where group members worked individually without other members present.
Day
Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
|  | 1 | 2 | 3 | 4 Group work session on Testing document 2:30pm-4:00pm | 5 Group work session on Testing document 2:00pm-5:00pm
6 Group work session on Testing document plus build skeleton for our project (create classes in Design document) 1:00pm-4:00pm | 7 | 8 | 9 | 10 | 11 | 12 Beginning implementation of Classes in our skeleton project. 2:30 - 6:00pm
13 Continued Classes implementation. Work Breakdown: Mackenzie work on shoot function, Mitch work on Main Menu/Team Selection, Ryan work on game properties panel, Will work on movement function. 1:30pm - 6:00pm | 14 | 15 Continued Classes implementation. Will and Mitch present. Will continued work on movement, Mitch work on main menu button mapping to controller. 3:00pm -4:00pm | 16 Continued Classes implementation. Work Breakdown: Mitch works on fixing main menu, Ryan implements Help panel, Mackenzie and Mitch Paired Programming session to finish move, shoot, receive dameage functions, and then begin gameboard testing 4:00pm-10:30pm | 17 | 18 Continued Classes implementation. Work Breakdown: Mackenzie fully implemented JSON interpreter and associated functions, beginning testing troubleshooting. Mitch beginning work on drawing hex spaces from hex class, Ryan finished game properties panel. 1:00pm-5:00pm | 19 Continued Classes implementation. Work Breakdown: Mackenzie continues testing of JSON interpreter, Mitch work on Main Menu/Team Selection, Ryan work on game properties panel, Will work on AI movement function and scan 2:00pm-6:30pm
20 | 21 Continued Classes implementation. Work Breakdown: Mackenzie created WordTranslator class to work with the interpreter parsing forth code. Mitch began more work on the Game panel, Ryan and Justin Paired Programming Session to get values from game panel accessable to controller, Will created anonymous functions for Wordtranslator | 22 | 23 Continued Classes implementation. Work Breakdown: Mackenzie paired programming with Will implementing basic WordTranslator functions with calls to robot functions and loops. Ryan concentating on drawing of the gameboard. Justin creating functions to determine enemy direction | 24 Continued Classes implementation. Work Breakdown: Mackenzie and Will continue pair programing for the Interpreter deciphering Forth codes. Ryan concentating on drawing of the gameboard and paired programmed with Mitch. Justin creating functions to determine enemy range. CODING REVIEW SESSION from 5:00pm to 7:00pm. Entire work session lasted from 1:00pm - 10:00pm | 25 Focus shift from class implementation to game play mechanics. Mackenzie creates classes to generate playable teams and set teams on the appropriate spaces on the gameboard. Will continues work on the WordTranslator and Interpreter classes. Ryan generates robot pictues for each class. Mackenzie and Ryan pair program to fix movement of robots on the gameboard. | 26 Continued work on functional game. Mackenzieand Ryan pair program to get team generation and player placement set up correctly, making sure robots shoot and move correctly and that robots are removed from the game when killed (only for human players). Will continues work on the WordTranslator and Interpreter classes. Mitch implements key functionality and mouse clicking to shoot. Work session from noon till 10:00pm
27 Continuing work on functional game. Mackenzie and Ryan work on furthing bug fixes to game play and player turns; implementing AI players into the game; Winner and Stats panel functionality. Mackenzie begins work on the putting together the coding document from everyone's paragraphs. Will continues work on the Interpreter to allow for functions. Mitch updates Team Selection Panel to have all buttons work correctly. Session from 11:00am - 9:30pm | 28 | 29 | 30 | 1 | 2 | 3 Finishing touches added to the game. Mackenzie and Mitch pair-programmed to make the Team selection panel up and operational. Ryan focuses on implementing Health stats for each player on screen. Justin makes formating adjustments so we are coniststant with our coding style. Will continues work on the interpreter and wordTranslator functions. Session from 1:30pm-6:30pm
4 Continuing work from previous day. Mackenzie Power and Mitch pair program to make team selection functional. Ryan implements current turn function. Will continues work on the Interpreter to work with loops and do statements. Work session from 3:00pm-8:30pm | 5 Fixes to problems involving AI functinaity on the gameBoard. Mackenzie and Ryan pair programed to fix these bugs and also implement a functional Stats panel. Will made changes to the scan and range functions. Session from noon - 9:30pm | 6 | 7 | 8 | 9 Mackenzie, Ryan, and Will work on submission and finishing up the programing and user manual. Session from 1:30pm-